## Sheet1
Sprint Backlog | [9 empty] | Estimated Time | Time Took
Id | Task | Responsible Person | Time Estimate | Time Took | Progress |  | time |  | Start | 240 | 240
ID | SPRINT 1 | [5 empty] | 26 |  | Sprint 1 | 200 | 214
7 | [6 empty] | 46 |  | Sprint 2 | 160 | 168
7.1 | Create tables for User, Room in MySQL | Ahmad & Athar | 3 | 4 | 100% |  | 45 |  | Sprint 3 | 120 | 123
7.2 | Create database in MySQL | Ahmad | 1 | 1 | 100% |  | 33 |  | Sprint 4 | 90 | 90
7.3 | Develop client webservice request using Retrofit library for Android | Deniz | 4 | 6 | InProgress |  | 34 |  | Sprint 5 | 50 | 56
7.4 | Connect UI elements to webservice | Amin & Ugurcan | 3 | 4 | InProgress | 25 | 51 |  | Sprint 6 | 0 | 0
2.2 | Build webservice using RETSful using JAX-RS on netbeans | Ahmad | 8 | 9 | 100% |  | 235
7.5 | Develop web service using Glassfish application server version 3 | Ahmad | 4 | 4 | 100% |  | 143
7.6 | Test Database | Athar | 1 | 1 | 100%
7.7 | Test Server | Ahmad | 1 | 1 | 100%
44
2 | [5 empty] | 10
2.1 | Create table for Post in MySQL | Ahmad | 1 | 1 | 100% | 21
2.2 | Add webservice for posting | Ahmad | 2 | 2 | 100% | 10
2.3 | Test UI | Amin | 1 | 1 | 100% | 7
19
8 | [5 empty] | 1
8.1 | Add cross-tables and vote tables in MySQL | Firat | 2 | 2 | 100%
8.2 | Android UI for voting | Amin | 6 |  | InProgress
21
21.1 | Android UI front page using Cardview and Cardslib library in Android Studio | Amin | 2 | 2 | 100%
21.2 | Webservice for getting posts with most votes | Ahmad | 2 | 2 | InProgress
20
20.1 | Navigation drawer as a sidebar showing main menu for Android | Amin | 1 | 2 | InProgress
13
13.1 | Android UI room page using Cardview and Cardslib library in Android Studio | Amin | 2 | 2 | InProgress
13.2 | Webservice for getting room details | Ahmad | 3 | 2 | InProgress
ID | SPRINT 2
7
7.3 | Develop client webservice request using Retrofit library for Android | Deniz | 4 | 6 | 100%
7.4 | Connect UI elements to webservice using JSON | Amin & Ugurcan | 3 | 4 | 100%
7.8 | Webservice for users and rooms using RETSful using JAX-RS on NetBeans | Ahmad & Firat | 2 | 2 | 100%
8
8.2 | Android UI for voting | Deniz | 2 | 1 | 100%
8.3 | Webservice for users to vote on post and comments on RETSful using JAX-RS | Ahmad & Firat | 2 | 2 | 100%
8.4 | Testing database consistancy for voting on webservice on NetBeans and MySQL | Athar | 2 | 2 | 100%
8.5 | Connection between UI and Webservice using JSON | Amin & Deniz | 4 | 3 | 100%
40
21
21.2 | Webservice for getting posts with most votes | Ahmad & Firat | 3 | 3 | InProgress
20
20.1 | Navigation drawer as a sidebar showing main menu for Android | Amin & Deniz | 2 | 2 | 100%
13
13.1 | Android UI room page using Cardview and Cardslib library in Android Studio | Amin & Deniz | 2 | 2 | 100%
13.2 | Webservice for getting room details | Ahmad | 3 | 2 | 100%
11
11.1 | Check username-password and profile status(active-deactive) | Ugurcan | 1 | 1 | InProgress
11.2 | Design pop-up box for login in UI | Ugurcan & Amin | 2 | 2 | InProgress
4
4.1 | Create tables in MySQL for commenting on posts | Ahmad & Athar | 1 | 1 | 100%
4.2 | Webservice for getting posts and comments' details | Ahmad | 3 | 2 | 100%
4.3 | Test database and webservice for commenting | Athar | 1 | 1 | 100%
5
5.1 | Create tables in MySQL for commenting on comments | Ahmad & Athar | 1 | 1 | 100%
5.2 | Webservice for getting posts and comments' details | Ahmad | 1 | 1 | 100%
5.3 | Test database and webservice for commenting for comments | Athar | 1 | 1 | 100%
ID | SPRINT 3 | Responsible Person | Time Estimate | Time Took | Progress
2
2.4 | Build webservice using RETSful using JAX-RS on netbeans (Create Post Service) | All | 8 | 10 | 100%
2.5 | Webservice for getting posts with most votes or timestamp in frontpage | Amin & Deniz | 1 | 2 | 100% | 30
2.6 | Library replacement for NavigationDrawer in Android Studio | Amin & Deniz | 3 | 5 | 100%
2.7 | WebService development for getting Post and Room contents | Ahamd & Athar | 5 |  | InProgress
2.9 | UI Development for posting | Amin | 2 |  | InProgress
2.9.1 | Using ExpandableLayout in PostContent Page | Deniz & Firat & Ugurcan | 4 |  | InProgress |  | 38
2.9.2 | Pull-to-refresh (SwipeRefreshLayout) | Deniz & Firat & Ugurcan | 3 | 3 | 100% |  | 49
21
21.2 | Webservice for getting posts with earliest timestamp in frontpage | All | 3 | 3 | 100%
21.3 | UI Development for Frontpage for showing latest post | Amin & Deniz | 3 | 3 | 100%
20
20.1 | Navigation drawer as a sidebar showing main menu for Android | Amin | 3 | 3 | 100%
13
13.1 | Android UI room page using Cardview and Cardslib library in Android Studio | Amin & Deniz | 4 | 5 | 100%
13.2 | Webservice for users to follow rooms | Amin & Ahmad & Athar | 3 | 6 | 100%
13.3 | Android UI development for users to follow rooms | Amin & Deniz & Firat&Ugurcan | 3 |  | InProgress
7
7.9 | Webservice for getting room list | Amin & Athar | 2 | 3 | 100%
7.10. | Library replacement for NavigationDrawer in Android Studio | Amin & Deniz | 2 | 2 | 100%
7.11 | Android development for retriving room list | Amin & Deniz | 2 | 2 | 100%
7.12 | Webservice for getting room details (Posts, Comments of post and votes) | Amin & Ahamd & Athar | 2 | 2 | 100%
7.13 | Android development for retriving room details (Posts, Comments of post and votes) | Amin | 2 | 3 | 100%
7.14 | Webservice for getting creating room | Ahmad & Athar | 5 |  | InProgress
7.15 | Android development creating room | Amin & Deniz & Firat&Ugurcan | 5 |  | InProgress
14
14.1 | Database support for users for following users | Ahmad & Athar | 1 | 1 | 100%
14.2 | Webservice for users to follow other users | Ahmad & Athar | 3 |  | InProgress
14.3 | Android development for following users | Amin & Deniz & Firat&Ugurcan | 6 |  | InProgress
ID | SPRINT 4 | Responsible Person | Time Estimate | Time Took | Progress
2
2.7 | WebService development for getting Post and Room contents | Ahamd & Athar | 5 | 2 | 100%
2.9 | UI Development for posting | Amin | 2 | 2 | 100%
2.9.1 | Using ExpandableLayout in PostContent Page | Deniz & Firat & Ugurcan | 4 | 4 | 100%
10
10.1 | WebService development for getting Vote | Amin & Ahamd & Athar | 2 | 2 | 100%
10.2 | UI Development for Votes | Amin | 1 | 1 | 100%
10.3 | WebService development for setting Vote | Amin | 1 | 1 | 100%
1
1.1 | WebService development for signup | Amin & Deniz | 4 | 4 | 100%
1.2 | Webservice for checking User | Amin & Ahamd & Athar | 1 | 1 | 100%
1.3 | Android development for signup page | Ugurcan & Firat | 2 | 2 | 100%
11
11.1 | WebService development for Login | Amin & Deniz | 1 | 1 | 100%
11.2 | Webservice for checking User | Amin & Ahamd & Athar | 1 | 1 | 100%
11.3 | Android development for Login page | Ugurcan & Firat | 1 | 1 | 100%
22
22.1 | WebService development for getting post with high number of votes in frontpage | All | 2 | 2 | 100%
16
16.1 | Webservice development for getting hall content for every user | All | 3 | 2 | 100%
16.2 | Webservice development for getting room content for every user | All | 3 | 2 | 100%
7
7.14 | Webservice for getting room content and creating room by user | Ahmad & Athar | 2 |  | InProgress |  | 7 | 48
7.15 | Android development creating room | Amin & Deniz & Firat&Ugurcan | 2 |  | InProgress
13
13.3 | Android UI development for users to follow rooms | Amin & Deniz & Firat&Ugurcan | 3 |  | InProgress
14
14.2 | Webservice for users to follow other users | Ahmad & Athar | 3 |  | InProgress
14.3 | Android development for following users | Amin & Deniz & Firat&Ugurcan | 6 |  | InProgress
ID | SPRINT 5 | Responsible Person | Time Estimate | Time Took | Progress
7
7.14 | Webservice for getting room content and creating room by user | Ahmad & Athar | 5 | 3 | 100%
7.15 | Android development creating room | Amin & Deniz & Firat&Ugurcan | 5 | 3 | 100%
13
13.3 | Android UI development for users to follow rooms | Amin & Deniz & Firat&Ugurcan | 2 | 2 | 100% | 34
13.4 | Webservice for users to follow rooms | Ahmad & Athar | 1 | 2 | 100% | 31
14
14.2 | Webservice for users to follow other users | Ahmad & Athar | 3 |  | InProgress
14.3 | Android UI development for following users | Amin & Deniz & Firat&Ugurcan | 6 |  | InProgress
9
9.1 | Websevice for users to vote for comments | Ahmad & Athar | 2 | 2 | 100%
9.2 | Android UI development for users to vote for comments | Amin & Deniz & Firat&Ugurcan | 3 | 2 | 100%
23
23.1 | Webservice for getting profile for users | Ahmad | 3 | 2 | 100%
23.2 | Android UI development for profile of users | Firat & Ugurcan | 2 | 2 | 100%
24
24.1 | Webservice for editing profile information for users | Ahmad & Firat & Ugurcan | 1 | 1 | 100%
24.2 | Webservice for editing credentials (password or username) | Ahmad & Firat & Athar | 1.5 | 2 | 100%
24.3 | Android UI development for editing information of users | Amin & Deniz | 1.5 | 2 | 100%
17
17.1 | Webservice for users to view other user's profile | Ahmad & Ugurcan | 2 | 2 | 100%
17.2 | Android UI development for viewing profile of other users | Amin & Deniz & Firat&Ugurcan | 2 | 3 | 100%
18
18.1 | Webservice for user to manage followers | All | 2 | 1 | InProgress
18.2 | Webservice for user to manage their posts and subcritions | All | 2 |  | InProgress
18.3 | Android UI development for profile editing | All | 2 |  | InProgress
25
25.1 | Webservice for getting validation email | Ahmad | 3 | 3 | 100%
ID | SPRINT 6 | Responsible Person | Time Estimate | Time Took | Progress
14
14.2 | Webservice for users to follow other users | Ahmad & Athar | 6 | 5 | 100%
14.3 | Android UI development for following users | Amin & Deniz & Firat&Ugurcan | 3 | 3 | 100% | 52
51
18
18.1 | Webservice for user to manage followers | All | 3 | 3 | 100%
18.2 | Webservice for user to manage their posts and subcritions | All | 3 | 2 | 100%
18.3 | Android UI development for profile editing | All | 3 | 3 | 100%
3
3.1 | Webservice for user for editing post | Ahmad& Firat& Ugurcan& Athar | 2 | 2 | 100%
3.2 | Database support for users to edit post | Ahmad & Athar | 1 | 1 | 100%
3.3 | Webservice for user for deleting post | Ahmad& Firat& Ugurcan& Athar | 2 | 2 | 100%
3.4 | Database support for users for deleting post | Ahmad & Athar | 1 | 1 | 100%
3.5 | Android development for editing post | Amin & Deniz & Firat | 2 | 2 | 100%
3.6 | Android development for deleting post | Amin & Deniz & Ugurcan | 1 | 1 | 100%
6
6.1 | Webservice for user for editing comment | Ahmad & Firat | 2 | 2 | 100%
6.2 | Database support for users to edit comment | Ahmad & Athar | 1 | 1 | 100%
6.3 | Webservice for user for deleting comment | Ahmad& Firat& Ugurcan& Athar | 1 | 2 | 100%
6.4 | Database support for users for deleting comment | Ahmad & Athar | 1 | 1 | 100%
6.5 | Android development for editing comment | Amin & Deniz & Firat | 1 | 1 | 100%
6.6 | Android development for deleting comment | Amin & Deniz & Ugurcan | 1 | 1 | 100%
15
15.1 | Webservice for searching in hall with database support | All | 7 | 7 | 100%
15.2 | Android development for providing search | All | 3 | 3 | 100%
12
12.1 | Webservice for user to deactivated account with database support | All | 5 | 5 | 100%
12.2 | Android development for user to deactivate account | All | 3 | 3 | 100%

## Sheet2
Product Backlog Item | Estimated Completion Time | Actual Time Spent
7 | 54 | 54
8 | 14 | 10
2 | 30 | 30
21 | 10 | 10
20 | 6 | 7
13 | 22 | 22
14 | 10 | 9
4 | 5 | 5
5 | 3 | 3
10 | 4 | 4
1 | 7 | 7
11 | 3 | 3
22 | 2 | 2
16 | 6 | 4
9 | 5 | 4
23 | 5 | 4
24 | 4 | 5
19 | 3 | 3
17 | 4 | 5
18 | 9 | 8
3 | 9 | 9
6 | 7 | 8
15 | 10 | 10
12 | 8 | 8
| 240 | 234