## Sheet1
Product Backlog
|  |  |  | Status | Priorty
ID | Story | Priorty | Time Estimate |  | 1 - High
1 | User can register to the hall | 4 | 7 | Complete | 10 - Low
2 | User can post in room | 1 | 30 | Complete
3 | User can edit/delete posts | 2 | 8 | Not Started |  | 38
4 | User can comment on post | 2 | 5 | Complete
5 | User can comment on comment | 2 | 3 | Complete |  |  |  | Ideal Task Remaining | Actual Task Remaining
6 | User can edit/delete comment | 2 | 6 | Not Started |  |  | Start | 25 | 25
7 | User can create a room | 1 | 54 | Complete |  |  | Sprint 1 | 19 | 18
8 | User can vote for a post | 3 | 14 | Complete |  |  | Sprint 2 | 15 | 17
9 | User can vote for a comment | 3 | 5 | Complete |  |  | Sprint 3 | 10 | 17
10 | User can edit vote | 3 | 4 | Complete |  |  | Sprint 4 | 7 | 8
11 | Users can login to their account | 4 | 3 | Complete |  |  | Sprint 5 | 4
12 | Users can deactivate their account | 4 | 5 | Not Started |  |  | Sprint 6 | 0
13 | User can follow room | 5 | 22 | Complete
14 | User can follow other users | 5 | 10 | InProgress
15 | User can search in hall | 6 | 7 | Not Started
16 | User can browse hall and rooms | 4 | 6 | Complete
17 | User can view other user's profile | 6 | 4 | Complete
18 | User can manage posts and subcriptions | 6 | 6 | InProgress
19 | User can be selected as room administrator | 7 | 10 | Not Started
20 | User can change setting of their accounts | 8 | 6 | Complete
21 | User can view latest posts of rooms | 8 | 10 | Complete
22 | User can view latest posts by votes | 4 | 2 | Complete
23 | User can view their profile | 7 | 5 | Complete
24 | User can edit their profile setting and credentials | 7 | 4 | Complete
25 | User recives confirmation email for creating account | 8 | 3 | Complete
239