## Sheet1
Sprint Backlog
Id | Story | Responsible Person | Time Estimate | Time Took | Status
Sprint 1
1.0.1 | Meeting with the group members and customer | All | 1 | 2 | Complete
1.0.2 | Talk abour ideas and finalize the decision | All | 0.5 | 0.5 | Complete
1.0.3 | Assigning duties for first Sprint | Ahmad | 0.5 | 0.5 | Complete
1.0.4 | Creat Backlog sheet | Firat | 1 | 3 | Complete
1.1.1 | Create GitHub Account | Amin | 0.5 | 0.3 | Complete
1.1.2 | Install Required Tools | All | 4 | 5 | Complete
1.2.1 | Design the front page and post page using Cardview and Cardslib library | Amin & Deniz | 2 |  | Incomplete
1.2.1 | Navigation drawer as a sidebar showing main menu for App | Amin | 5 |  | Incomplete
1.3.1 | Design database in MySQL | Ahmad | 3 |  | Incomplete
1.3.2 | DB for User, Room, Post | Ahmad & Ugurcan | 3 |  | Incomplete
1.4.1 | Building server for communication with MySQL | Ahmad & Ugurcan | 2 |  | Incomplete
1.4.2 | Connect UI elements for communication | Ahmad & Amin | 3 |  | Incomplete
1.5.1 | Create the sprint backlog and product backlog | Athar |  |  | Incomplete
1.5.2 | Commit in GiutHub | All |  |  | Incomplete