## Sheet1
Product Backlog
|  |  |  | Status | Priorty
ID | Story | Priorty | Time Estimate |  | 1 - High
1 | User can register to the hall | 4 | 7 | Not Started | 10 - Low
2 | User can post in room | 1 | 30 | Complete
3 | User can edit/delete posts | 2 | 10 | Not Started
4 | User can write a comment on post | 2 | 10 | InProgress
5 | User can write a comment for comment | 2 | 6 | InProgress |  |  | Ideal Task Remaining | Actual Task Remaining
6 | User can edit/delete comment | 2 | 6 | Not Started |  | Start | 21 | 21
7 | User can create a room | 1 | 10 | Complete |  | Sprint 1 | 18 | 19
8 | User can vote for a post | 3 | 24 | Complete |  | Sprint 2 | 14
9 | User can vote for a comment | 3 | 10 | InProgress |  | Sprint 3 | 11
10 | User can edit vote | 3 | 7 | Not Started |  | Sprint 4 | 7
11 | Users can login to their account | 4 | 10 | InProgress |  | Sprint 5 | 4
12 | Users can deactivate their account | 4 | 5 | Not Started |  | Sprint 6 | 0
13 | User can follow room | 5 | 20 | InProgress
14 | User can follow other users | 5 | 8 | Not Started
15 | User can search in hall | 6 | 20 | Not Started
16 | User can browse hall and rooms | 4 | 20 | Not Started
17 | User can see notifications | 6 | 10 | Not Started
18 | User can manage followers, posts and subcriptions | 6 | 5 | Not Started
19 | User can be selected as room administrator | 7 | 6 | Not Started
20 | User can change setting of their accounts | 8 | 6 | InProgress
21 | User can view latest posts by users and rooms | 8 | 10 | InProgress
240