## Sheet1
Sprint Backlog
Id | Story | Responsible Person | Time Estimate | Time Took | Status
Sprint 1
1.0.0 | Creat Backlog sheet | Firat | 1 | 1 | Complete | 48
1.1.1 | Create GitHub Account | Amin | 0.5 | 0.5 | Complete | 54.5
1.1.2 | Install Required Tools | All | 6 | 7 | Complete
1.2.1 | Android UI front page, room page, post page using Cardview and Cardslib library in Android Studio | Amin & Deniz | 7 | 8 | Complete
1.2.2 | Navigation drawer as a sidebar showing main menu for Android | Amin | 4 | 3 | Complete
1.2.3 | Develop client webservice request using Retrofit library for Android | Deniz | 4 | 6 | InProgress
1.3.1 | Create database in MySQL | Ahmad | 5 | 4 | Complete
1.3.2 | Create tables for User, Room, Post in MySQL | Ahmad & Firat | 4 | 5 | Complete
1.3.3 | Add cross-tables and vote tables in MySQL | Firat | 2 | 2 | Complete
1.4.1 | Build webservice using RETSful using JAX-RS on netbeans | Ahmad | 4 | 6 | Complete
1.4.2 | Develop web service using Glassfish application server version 3 | Ahmad | 3 | 2 | Complete
1.4.3 | Connect UI elements for communication | Ahmad & Amin | 3 | 4 | InProgress
1.5.1 | Create the sprint backlog and product backlog | Athar | 2 | 2 | Complete
1.5.2 | Commit in GiutHub | All | 1 | 2 | Complete
1.5.3 | Add wiki for repositories | Athar & Ugurcan | 1.5 | 2 | Complete