## Sheet1
Sprint Backlog | [8 empty] | Estimated Time | Time Took
Id | Task | Responsible Person | Time Estimate | Time Took | Progress | time |  | Start | 240 | 240
ID | SPRINT 1 |  |  |  |  | 47 |  | Sprint 1 | 200 | 207
7 | [5 empty] | 39 |  | Sprint 2 | 160 | 159
7.1 | Create tables for User, Room in MySQL | Ahmad & Athar | 3 | 4 | 100% |  |  | Sprint 3 | 120
7.2 | Create database in MySQL | Ahmad | 1 | 1 | 100% |  |  | Sprint 4 | 80
7.3 | Develop client webservice request using Retrofit library for Android | Deniz | 4 | 6 | InProgress |  |  | Sprint 5 | 40
7.4 | Connect UI elements to webservice | Amin & Ugurcan | 3 | 4 | InProgress |  |  | Sprint 6 | 0
2.2 | Build webservice using RETSful using JAX-RS on netbeans | Ahmad | 8 | 9 | 100%
7.5 | Develop web service using Glassfish application server version 3 | Ahmad | 4 | 4 | 100%
7.6 | Test Database | Athar | 1 | 1 | 100%
7.7 | Test Server | Ahmad | 1 | 1 | 100%
2
2.1 | Create table for Post in MySQL | Ahmad | 1 | 1 | 100%
2.2 | Add webservice for posting | Ahmad | 2 | 2 | 100%
2.3 | Test UI | Amin | 1 | 1 | 100%
8
8.1 | Add cross-tables and vote tables in MySQL | Firat | 2 | 2 | 100%
8.2 | Android UI for voting | Amin | 2 | 1 | InProgress
21
21.1 | Android UI front page using Cardview and Cardslib library in Android Studio | Amin | 2 | 2 | 100%
21.2 | Webservice for getting posts with most votes | Ahmad | 2 | 2 | InProgress
20
20.1 | Navigation drawer as a sidebar showing main menu for Android | Amin | 1 | 2 | InProgress
13
13.1 | Android UI room page using Cardview and Cardslib library in Android Studio | Amin | 2 | 2 | InProgress
13.2 | Webservice for getting room details | Ahmad | 3 | 2 | InProgress
ID | SPRINT 2
7
7.3 | Develop client webservice request using Retrofit library for Android | Deniz | 4 | 6 | 100%
7.4 | Connect UI elements to webservice using JASON | Amin & Ugurcan | 3 | 4 | 100%
7.8 | Webservice for users and rooms using RETSful using JAX-RS on NetBeans | Ahmad & Firat | 2 | 2 | 100%
8
8.2 | Android UI for voting | Deniz | 2 | 1 | 100%
8.3 | Webservice for users to vote on post and comments on RETSful using JAX-RS | Ahmad & Firat | 2 | 2 | 100%
8.4 | Testing database consistancy for voting on webservice on NetBeans and MySQL | Athar | 2 | 2 | 100%
8.5 | Connection between UI and Webservice using JASON | Amin & Deniz | 4 | 3 | 100%
40
21
21.2 | Webservice for getting posts with most votes | Ahmad & Firat | 3 | 3 | InProgress
20
20.1 | Navigation drawer as a sidebar showing main menu for Android | Amin & Deniz | 2 | 2 | 100%
13
13.1 | Android UI room page using Cardview and Cardslib library in Android Studio | Amin & Deniz | 2 | 2 | 100%
13.2 | Webservice for getting room details | Ahmad | 3 | 2 | 100%
11
11.1 | Check username-password and profile status(active-deactive) | Ugurcan | 1 | 1 | InProgress
11.2 | Design pop-up box for login in UI | Ugurcan & Amin | 2 | 2 | InProgress
4
4.1 | Create tables in MySQL for commenting on posts | Ahmad & Athar | 1 | 1 | 100%
4.2 | Webservice for getting posts and comments' details | Ahmad | 3 | 2 | 100%
4.3 | Test database and webservice for commenting | Athar | 1 | 1 | 100%
5
5.1 | Create tables in MySQL for commenting on comments | Ahmad & Athar | 1 | 1 | 100%
5.2 | Webservice for getting posts and comments' details | Ahmad | 1 | 1 | 100%
5.3 | Test database and webservice for commenting for comments | Athar | 1 | 1 | 100%

## Sheet2
Product Backlog Item | Estimated Completion Time | Actual Time Spent
7 | 9 | 12
8 | 10 | 8
11 | 3 | 3
21 | 3 | 3
20 | 2 | 2
13 | 5 | 4
4 | 5 | 4
5 | 3 | 3